## Slide 1
25+ YEARS OF EXPERIENCE.
360° OF VISION, EXECUTION + SUPPORT.
ONE TRUSTED TRANSFORMATION PARTNER.
Deliver Oracle Projects Using Vigilant's Application Delivery Guidelines

## Slide 2
Application Delivery Guidelines
Choosing the Right Project Type
Operating the Three-Role Delivery Model
Preparing the Functional Document Set
Controlling Technical and Conversion Deliverables
Running Discovery, Solution Build, and CRP
Testing the Solution and Going Live
Topics covered in this session:
Choosing the Right Project Type
Operating the Three-Role Delivery Model
Preparing the Functional Document Set
Controlling Technical and Conversion Deliverables
Running Discovery, Solution Build, and CRP
Testing the Solution and Going Live

## Slide 3
Matching Work to Implementation, Rollout, or Upgrade
Implementation/Transformation deploys Oracle Fusion or EBS end to end - redesign, configuration, conversion, integrations, testing, go-live
Rollout extends an existing implementation to new geographies, business units, or legal entities using the global template
Rollouts add localized configurations, data, and statutory requirements - the template itself stays predefined
Upgrade moves EBS or Fusion to a newer release - impact assessment, customization remediation, regression testing
Implementation / Transformation
Rollout
Upgrade
Assessment
Enhancement
Managed Support
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 4
Scoping Assessments, Enhancements, and Managed Support
Assessment is a short-term advisory engagement - system health, fit-gap, performance, security, or upgrade readiness
Every assessment ends in actionable recommendations, not a build
Enhancement delivers targeted improvements - reports, integrations, dashboards, workflows, extensions - without full reimplementation
Managed Support runs post go-live - incidents, minor enhancements, monitoring, patches, and continuous improvement
Assessment
Enhancement
Managed Support
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 5
Assigning Accountability Across Three Role Categories
Enterprise Architect is accountable for the overall outcome - solution integrity, client success, major decisions, Go-Live recommendation
Project Manager / PMO owns the integrated plan, governance, budget and forecast tracking, RAID management, reporting
Workstream Delivery Team owns detailed discovery, design, configuration, development, conversion, and testing in its workstream
The workstream team includes the Module Head (SME), Functional and Technical Architects, Consultants, and Developers
Enterprise Architect
Project Manager / PMO
Workstream Delivery Team
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 6
Respecting Role Boundaries and Escalation Rules
The EA does not perform every detailed task - the EA ensures owners are assigned, decisions made, quality acceptable
The PM does not own functional, technical, or architecture decisions - only that each has an owner, due date, and escalation path
Workstream Leads cannot change approved scope, design direction, or committed dates without EA and PM governance
Material scope, budget, or Go-Live trade-offs need EA recommendation, PM impact assessment, and client or Steering Committee approval
EA recommends
PM assesses impact
Steering Committee approves
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 7
Tracking Accountability Through Each Phase
The EA validates the SOW at Mobilization and gates entry into CRP, SIT, UAT, Cutover, and Hypercare
PM/PMO artifacts: Project Charter, integrated plan, RAID and Change Control logs, Cutover Plan, Go-Live Readiness Checklist
Workstream Leads answer for quality and timely completion of deliverables per the Document Accountability Matrix
The Go-Live recommendation must be supported by objective readiness evidence, with exceptions assessed and documented
Mobilization
Discovery
Solution Build
SIT / UAT
Cutover
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 8
Capturing Requirements in the RTM
Only Functional Architects prepare and update the RTM - Functional SMEs review and route feedback back for updates
Notes follow "MM/DD Initials: Comment" and are never overwritten - they serve as minutes of meeting
Fill Summarized Requirements only after the requirement is understood - every row must eventually be populated
Row-level approval finalizes requirements incrementally - all rows Approved and baselined before SIT begins
Capture dated notes
Summarize requirement
Requires Approval
Approved
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 9
Writing the SDD, CWB, and Process Flows
Functional SMEs write the SDD mapping requirements to Oracle features - approved before SIT, after CRP sign-off
The Configuration Workbook records every setup value - single source of truth, approved before PROD
Visio flows use the Vigilant template as-is - left to right, inputs to outputs, no Start/End symbols
Green arrow means yes, red means no - and each process shows Oracle Standard, Custom/Extension, or Manual/Offline
SDD
Configuration Workbook
Process Flows
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 10
Running Workshops and Recording Design Decisions
The WDD is a client-agnostic deck per module - copy it per project, review internally with SDM or PM before presenting
The FKDD records each decision - options with pros and cons, the team's recommendation highlighted green, approver and date
Every approved decision is also summarized in the RAID log by the Functional Architect
Approved decisions bind the SDD, configuration, development, and testing - changes need formal change control
Present options
Business decides
Record in FKDD
Summarize in RAID
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 11
Preparing Change Impact, Test Scripts, and Training Manuals
The CIAD documents only what changes - AS-IS versus TO-BE, impacted roles - finalized before training and UAT
Test scenarios are realistic Day-in-the-Life flows, business-approved before SIT execution
Functional SMEs write scripts and map them to scenarios; Functional Architects verify coverage
Training Manuals reflect only approved functionality and never substitute for the RTM or SDD
CIAD
Test Scripts
Training Manuals
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 12
Maintaining the RICEFW Inventory and TRDDs
RICEFW covers Reports, Integrations, Conversions, Extensions, Forms, Workflows - the Technical Solution Architect owns the inventory
The inventory is baselined before development and finalized before PROD - every scope change goes through change control
One TRDD per component - Functional SMEs write the business context, Technical Developers the technical design
TRDDs must not introduce new functional requirements - all scope traces back to approved requirements
Log in RICEFW
Write TRDD
Approve
Develop
Unit test
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 13
Recording Architecture Decisions and Technical Flows
The TKDD is one deck per project for program-level decisions - object-level design stays in the TRDD
Present at least two options where feasible, with risks - Enterprise Architect and Service Delivery Manager review
Decisions must be approved before impacted development and reaffirmed before production deployment
Technical Architecture Process Flows in Visio show system interactions, data direction, error handling, and security touchpoints
TKDD - program level
TRDD - object level
Architecture Flows
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 14
Migrating Code and Proving Unit Tests
The Code Migration Document tracks every promotion with deployment steps, rollback plan, owner, and approver
The UAT package is the production package - no code changes, recompilations, or manual fixes between UAT and PROD
UAT defects are fixed in non-UAT development environments, then the package is redeployed to UAT first
Only Pass unit-test components promote to SIT or UAT - exceptions need Technical Solution Architect approval
DEV
TEST
UAT
PROD
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 15
Defining Conversion Rules in the CRD
The CRD covers source-to-target mappings, transformation, cleansing, defaulting logic, load sequencing, and reconciliation rules
Prepared by the Conversion SME - reviewed by the Conversion Lead, Functional SMEs, and Technical Solution Architect
Approved before conversion development, validated by business data owners during mock conversions
Final CRD approval is required before the production cutover conversion - data quality stays a shared responsibility
Map source to target
Approve CRD
Sample conversion
Business validation
Cutover load
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 16
Laying the Foundation in Discovery
Understand AS-IS processes through facility visits and interviews - capture pain points and high-level requirements in the RTM
Design the enterprise structure - legal entities, ledgers, business units, Chart of Accounts - via WDD and FKDD sessions
Collect real sample data - actual suppliers, customers, items, pricing - never demonstrate with "Test Supplier"
Functions outside the future state get a high-level discussion, then a deep dive or "Not Applicable" in the RTM
Study AS-IS
Gather requirements
Design enterprise structure
Establish governance
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 17
Planning and Running Solution Build Workshops
Review the RTM Meeting Agenda sheet first - it lists workshop topics and hours; prepare one if it is missing
Set the cadence with PMO - 80 workshop hours in 20 working days means a four-hour session every day
Demonstrate Oracle standard functionality and use RTM questions to guide - understand the need, not just record answers
Additional sessions are exceptions to raise with PMO - ad hoc meetings only for unexpected issues
Check Meeting Agenda
Schedule cadence
Demonstrate capability
Refine until agreed
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 18
Approving Requirements Row by Row
Standard fit, no gap: record "Standard Functionality Accepted" - not applicable: record "Capability Not Required"
Set the status to Requires Approval and email the RTM row numbers after each meeting
The client adds initials and date in Notes, then flips the status to Approved
Mark each row Fit or Gap - blank Summarized Requirements while sessions progress is a project warning
Summarize requirement
Requires Approval
Client reviews
Approved
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 19
Validating End to End in CRP
CRP presents the agreed design as integrated end-to-end processes with custom roles and available RICEFW components
Log feedback in the CRP Issue Tracker - distinguish defects, design changes, new requirements, and training issues
Run the first sample data conversion - reconcile record counts, balances, and key attributes with the business
CRP sign-off baselines and locks requirements and design for SIT and UAT - later changes need formal change control
Demonstrate end-to-end
Track issues
Resolve and re-demo
Sign off and baseline
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 20
Executing System Integration Testing
Run the Full Load SIT conversion, then Vigilant readiness testing so no system-level issues block testers
Scenarios are Day-in-the-Life sequences - approvals, exceptions, corrections, inquiries, reporting - business-approved before execution
The same scenario library serves SIT and UAT, with execution adjusted for each phase's purpose
Log every defect in the agreed tool - retest, regression test, then obtain UAT readiness sign-off
Deploy SIT build
Full Load conversion
Readiness testing
Execute and fix
UAT readiness sign-off
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 21
Running Day-in-the-Life UAT
UAT simulates a typical day or week of operations - not a checklist walk through test scripts
Vigilant runs readiness testing first so system-level issues are resolved before business users start
Assign scenarios by users' actual roles - realistic data, volumes, approvals, exceptions, corrections, reporting
Classify issues as defects, training gaps, data issues, or change requests - each follows a different path
Full Load conversion
Readiness testing
Train users
Day-in-the-Life execution
UAT sign-off
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 22
Executing Production Cutover
Pre-Blackout: migrate configurations, deploy RICEFW components, convert master data - keep everything dormant until Go-Live
Clone Production after deployment and smoke test critical flows - apply every fix in both clone and Production
Blackout Cutover: incremental master data, open transactions and balances, final reconciliation, then enable access
Execute the Cutover Plan and Go-Live Readiness Checklist, validate critical transactions, obtain final Go-Live approval
Pre-Blackout deploy
Clone and smoke test
Blackout Cutover
Reconcile and validate
Go-Live approval
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Slide 23
Thank you for your time.
Collaborative Transformation Awaits.
Contact Us
Email
Phone
info@vigilant-inc.com
+1-866-896-7755
Website
www.vigilant-inc.com